## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 18Q4
Reported by | Matt Doidge
Progress over last Quarter
Site |  | Successes |  |  | Problems/Issues
Liverpool | Deployment research Storage Sysadmin. | HTCondor-CE in production Fixes, test and document for APEL-client for HTCondor-CE Preprations in puppet for DPM conversion to DOME Revert VAC to SL6. C7 gives kernel lockup. Varied sysadmin (CVEs, kernel updates, etc. Bids for new HW order |  |  | Having problems with older HW, esp migration to C7. Need to document route to HTCondor-CE for other sites.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Liverpool | Older hardware is hard to get going with CentOS7. |  |  | Use for VAC, sl6.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | Adoption of Ipv6, documentation HW Purchase (CPU, Disk) LSST changes (see af email, 22 Oct) VAC Superslot/Multicore tests Condor/Singularity, document baseline HTCondorCE Acc parsers release Find reason for VAC/C7 deadlock. Adoption of Ipv6, documentation |  |  | 31 Dec 2018 31 Dec 2018 31 Dec 2018 31 Dec 2018 31 Dec 2018 31 Dec 2018 31 Dec 2018 31 Dec 2018 |  | External partners unready Bids out. Next step is to order. Complete Deferred Complete Complete Deferred Deferred
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | Deal with CentOS7 on older hardware problems Remove all SL6 resources Set up new hardware Document route to HTCondor-CE Switch DOME on Remove BDII dependency for APEL client |  |  | 1 Apr 2019 1 Apr 2019 1 Apr 2019 1 Apr 2019 1 Apr 2019 1 Apr 2019 |  | No SL6 No SL6 New slots and storage running New doc to help sites DOME running APEL works without BDII
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Ste working with STFC/WLCG Accounting on support for HTCondorCE parser. |  |  | 1 Sept 2018 |  | Now in operation
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes